## Tabelle1
Task | Start date | Due date | Duration
Milestone: Submission Implementation | 2022-03-31 | 2022-03-31 | 1
Implementation | 2021-11-01 | 2022-03-31 | 151
Milestone:Submission prototype | 2021-10-31 | 2021-10-31 | 1
Implement Prototype | 2021-10-17 | 2021-10-31 | 15
Milestone: presentation | 2022-04-30 | 2022-04-30 | 1
Prepare Presentation | 2022-04-01 | 2022-04-30 | 30
Milestone: Submission of final version of master thesis | 2022-03-31 | 2022-03-31 | 1
Corrections and rewriting | 2022-03-01 | 2022-03-31 | 31
Milestone: Submission first version of master thesis | 2022-02-28 | 2022-02-28 | 1
Editing and re-writing master thesis | 2022-02-14 | 2022-02-28 | 15
Writing chapters Evaluation + Summary + Discussion chapters | 2022-01-01 | 2022-01-15 | 15
Writing chapter Approach | 2021-12-01 | 2021-12-31 | 31
Wiriting chapters Introduction + Related work + Bachground | 2021-11-16 | 2021-11-30 | 15
Further Research | 2021-11-01 | 2021-11-15 | 15
Writing the proposal | 2021-10-01 | 2021-10-31 | 31
Theoretical part
Practical part/ Implementation