## Tabelle1
Task | Start date | Due date | Duration
Milestone: Submission Implementation | 2022-03-31 | 2022-03-31 | 1 |  | Sprint 1 |  |  |  | Sprint 2 |  |  |  | Sprint 3 |  |  |  | Sprint 4 |  |  |  | Sprint 5
Further Improvements and Refactoring | 2022-03-15 | 2022-03-31 | 17 | Writing | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Implement Evaluation of the approach | 2022-02-15 | 2022-03-14 | 28 | Further research, writing first three chapters
Milestone: First working version of UCGAN | 2022-02-15 | 2022-02-15 | 1 | Writing chapter Approach
Implementation of Uncertainty Sampling | 2022-01-01 | 2022-02-14 | 45 | Writing chapter Implementation
Implementation of the score function | 2021-12-15 | 2021-12-31 | 17 | Writing Evaluation, Summary and Discussion
Implementation of score fct components | 2021-11-15 | 2021-12-15 | 31 | Milestone: Submission first version
First adjustment to the original approach | 2021-11-01 | 2021-11-14 | 14 | Corrections and rewriting
Milestone: Submission final version
Milestone: Submission final version | 2022-03-31 | 2022-03-31 | 1 | Implementation
Corrections and rewriting | 2022-03-01 | 2022-03-31 | 31 | Implementation of simple first version
Milestone: Submission first version | 2022-02-28 | 2022-02-28 | 1 | Development of further alternatives and improvements
Editing and re-writing master thesis | 2022-02-14 | 2022-02-28 | 15 | Definition and implementation of the final approach
Writing last three chapters | 2022-01-15 | 2022-02-13 | 30 | Milestone: Final structure of my approach is fixed
Writing chapter Approach | 2021-12-01 | 2022-01-15 | 46 | Implement Evaluation of the approach
Milestone: Finished quoting part | 2021-11-30 | 2021-11-30 | 1 | Further improvements and Refactoring
Writing first three chapters | 2021-11-16 | 2021-11-30 | 15 | Milestone: Submission Implementation
Further Research | 2021-11-01 | 2021-11-15 | 15
Theoretical part
Practical part/ Implementation