## Tabelle1
Task | Start date | Due date | Duration
Milestone: Submission Implementation | 2022-03-31 | 2022-03-31 | 1
Further Improvements and Refactoring | 2022-03-15 | 2022-03-31 | 17
Implement Evaluation of the approach | 2022-02-15 | 2022-03-14 | 28
Milestone: First working version of UCGAN | 2022-02-15 | 2022-02-15 | 1
Implementation of Uncertainty Sampling | 2022-01-01 | 2022-02-14 | 45
Implementation of the score function | 2021-12-15 | 2021-12-31 | 17
Implementation of score fct components | 2021-11-15 | 2021-12-15 | 31
First adjustment to the original approach | 2021-11-01 | 2021-11-14 | 14
Milestone: Submission final version | 2022-03-31 | 2022-03-31 | 1
Corrections and rewriting | 2022-03-01 | 2022-03-31 | 31
Milestone: Submission first version | 2022-02-28 | 2022-02-28 | 1
Editing and re-writing master thesis | 2022-02-14 | 2022-02-28 | 15
Writing last three chapters | 2022-01-15 | 2022-02-13 | 30
Writing chapter Approach | 2021-12-01 | 2022-01-15 | 46
Milestone: Finished quoting part | 2021-11-30 | 2021-11-30 | 1
Writing first three chapters | 2021-11-16 | 2021-11-30 | 15
Further Research | 2021-11-01 | 2021-11-15 | 15
Theoretical part
Practical part/ Implementation